## Status by Step
PROJECT STATUS BY WORKFLOW STEP - TUNNEL ANALYSIS v4.0
Osong Tunnel Monitoring Project ¦ CBNU Smart Structure Lab (SSL) ¦ Mirrors the current GUI sidebar (core mode) ¦ Code-verified 2026-06-08
ID | Module / Feature (GUI label) | Current Status | Priority | Current Code Status (evidence) | Remaining Work / Optimization
STEP 1 - LiDAR DATA ACQUISITION
1.1 | Import LAS / PLY data | COMPLETED | Medium | Parses .las/.laz/.ply and .txt/.xyz/.pts/.csv (io_layer.py); RGB->luminance fallback; multi-epoch (T0/Tn) load. | . Optional: native E57 / vendor headers (Trimble/Faro).
1.2 | Add scan station (+) | COMPLETED | Medium | Loads additional scanner stations into one context; coordinate frame preserved across multi-station merges. | .
STEP 2 - PREPROCESSING AND NOISE FILTERING
2.1 | Voxel downsampling | COMPLETED | Low | Open3D voxel grid; recenters only for a single scan so multi-station frames stay aligned. Adaptive SOR available. | . Numba JIT only worthwhile beyond ~50M points.
2.2 | Clean noise (auto: cables, lights, people, wall cables) | COMPLETED | Medium | auto_denoise(): removes cables (linearity), lights (sphericity), people (DBSCAN) via vectorized local-PCA Demantke features + sanity guards. Runs inside AUTO PIPELINE. | . Future: deep-learning segmentation (PointNet++) for hard cases.
STEP 3 - REGISTRATION AND SYNCHRONIZATION
3.1 | Auto-align T0/Tn epochs (target or ICP) | PENDING | High | register_epochs(): marker-SVD when >=3 fixed targets (no deformation absorption) else trimmed-ICP; divergence-guard keeps result never worse than input. | . Roll about a round tunnel needs markers; yaw+translation recovered by ICP.
STEP 4 - GEOMETRIC COORDINATE SYSTEM
4.1 | B-Spline C2 centerline (PDF 3.4) | COMPLETED | High | Scipy splprep/splev C2 trajectory + curvature-guarded tangent refine; builds gravity-anchored Bishop (twist-free) Frenet frames and intensity-derivative ring seams in the same pass. | (Bishop frame + intensity-valley ring seams implemented).
STEP 5 - PARAMETER EXTRACTION
5.1 | Crown settlement dv | PARTIALLY COMPLETE | High | calc_arch_settlement vs T0 per Frenet section; robust p99 crown (a stray slab point cannot inflate it); _has_t0_reference helper for single/dual-scan. | .
5.2 | Horizontal convergence dh | PARTIALLY COMPLETE | High | calc_horizontal_convergence vs T0; robust p99-p1 width (stray points cannot inflate the span). | .
5.3 | Ovality epsilon | PARTIALLY COMPLETE | High | Fitzgibbon Direct Least-Squares ellipse fit (fit_ellipse_fitzgibbon) -> real axes a,b; covariance-eigenvalue fallback only if the fit fails. | (Fitzgibbon DLS, not covariance eigenvalues).
5.4 | Section eccentricity e | PARTIALLY COMPLETE | High | Centroid-vs-axis offset; curved-tunnel single-scan eccentricity detrended (Kasa circle centre + moving-median) to remove false ~450mm bias. | . Curved 1-scan max ~245mm residual; load T0+Tn for exact result.
STEP 6 - TIME-SERIES ANALYSIS
6.1 | Plot deformation trend T0→Tn | PARTIALLY COMPLETE | High | Crown/convergence/ovality trend along chainage; forecast_threshold_crossing() predicts time-to-CAUTION/CRITICAL with R^2 (NEW, 15/15 tests). | Forecast engine ; GUI multi-epoch (3+) loading still to wire.
6.2 | M3C2 deformation map T0→Tn | PARTIALLY COMPLETE | High | M3C2 (py4dgeo) with C2C cKDTree fallback; multi-epoch spatiotemporal drift; Hausdorff heatmap green/yellow/red. | (KD-Tree multi-epoch drift).
6.3 | Plot 2D Technical Section T0/Tn | PARTIALLY COMPLETE | High | Runs the per-section clearance check (robust p1 flag + portal guard, no false alarms) and classify_sections() - the single source of truth (OK/CAUTION/CRITICAL) shared by ruler/track/3D/dashboard; banner now consistent with section alerts. | (clearance + banner hardened this session, 11 tests).
STEP 7 - BIM, REPORTING AND AI
7.1 | Export IFC tunnel structure | PARTIALLY COMPLETE | Medium | export_ifc(include_components=False): continuous tunnel lining as a tessellated shell (IfcPolygonalFaceSet) LOFTED from the measured per-section rings, so it follows real deformation (not a uniform-radius tube); hollow (outer+inner+end caps), status-coloured bands (grey/amber/red), + IFC4X3 IfcAlignment centerline. Per-section data kept as property sets. Cable/light geometry excluded per scope. | . Optional later: classify shell as IfcWall/IfcSlab/IfcSpace; IfcSectionedSolidHorizontal for fully parametric sweep.
7.2 | Export section CSV | PARTIALLY COMPLETE | Low | Per-section parameters exported to CSV for downstream integration. | .
7.3 | Export Excel report | PARTIALLY COMPLETE | Low | Multi-sheet Excel workbook of parameters and warnings. | .
7.4 | Export PDF report | PARTIALLY COMPLETE | Medium | reportlab PDF: cover, summary, charts, section table, warnings. | .
7.5 | Generate AI work order (PDF) | PARTIALLY COMPLETE | Medium | generate_work_order(): groups flagged sections into a ranked PDF work order (location, standard, action, priority); optional offline-safe LLM narrative (NEW, 26/26 tests). | .
7.6 | Query structural AI assistant | PARTIALLY COMPLETE | Low | RAG (ChromaDB + sentence-transformers) with Korean safety standards; query() injects serialized PipelineContext (RMSE, ovality, settlement) into the prompt; Ollama offline. | (context injection target met).
Legend:
| COMPLETED | implemented & verified in code/tests
| PARTIALLY COMPLETE | core works; enhancement remaining
| PENDING | not started