## Status by Step
PROJECT STATUS BY WORKFLOW STEP - TUNNEL ANALYSIS v4.0
Osong Tunnel Monitoring Project ¦ CBNU Smart Structure Lab (SSL) ¦ Mirrors the current GUI sidebar (core mode) ¦ Code-verified 2026-06-08
ID | Module / Feature (GUI label) | Current Status | Priority | Current Code Status (evidence) | Remaining Work / Optimization
STEP 1 - LiDAR DATA ACQUISITION
1.1 | Import LAS / PLY data | COMPLETED | Medium | Parses .las/.laz/.ply and .txt/.xyz/.pts/.csv (io_layer.py); RGB->luminance fallback; multi-epoch (T0/Tn) load. | Done. Optional: native E57 / vendor headers (Trimble/Faro).
1.2 | Add scan station (+) | COMPLETED | Medium | Loads additional scanner stations into one context; coordinate frame preserved across multi-station merges. | Done.
STEP 2 - PREPROCESSING AND NOISE FILTERING
2.1 | Voxel downsampling | COMPLETED | Low | Open3D voxel grid; recenters only for a single scan so multi-station frames stay aligned. Adaptive SOR available. | Done. Numba JIT only worthwhile beyond ~50M points.
2.2 | Clean noise (auto: cables, lights, people, wall cables) | COMPLETED | Medium | auto_denoise(): removes cables (linearity), lights (sphericity), people (DBSCAN) via vectorized local-PCA Demantke features + sanity guards. Runs inside AUTO PIPELINE. | Done. Future: deep-learning segmentation (PointNet++) for hard cases.
STEP 3 - REGISTRATION AND SYNCHRONIZATION
3.1 | Auto-align T0/Tn epochs (target or ICP) | COMPLETED | High | register_epochs(): marker-SVD when >=3 fixed targets (no deformation absorption) else trimmed-ICP; divergence-guard keeps result never worse than input. | Done. Roll about a round tunnel needs markers; yaw+translation recovered by ICP.
STEP 4 - GEOMETRIC COORDINATE SYSTEM
4.1 | B-Spline C2 centerline (PDF 3.4) | COMPLETED | High | Scipy splprep/splev C2 trajectory + curvature-guarded tangent refine; builds gravity-anchored Bishop (twist-free) Frenet frames and intensity-derivative ring seams in the same pass. | Done (Bishop frame + intensity-valley ring seams implemented).
STEP 5 - PARAMETER EXTRACTION
5.1 | Crown settlement dv | COMPLETED | High | calc_arch_settlement vs T0 per Frenet section; robust p99 crown (a stray slab point cannot inflate it); _has_t0_reference helper for single/dual-scan. | Done.
5.2 | Horizontal convergence dh | COMPLETED | High | calc_horizontal_convergence vs T0; robust p99-p1 width (stray points cannot inflate the span). | Done.
5.3 | Ovality epsilon | COMPLETED | High | Fitzgibbon Direct Least-Squares ellipse fit (fit_ellipse_fitzgibbon) -> real axes a,b; covariance-eigenvalue fallback only if the fit fails. | Done (Fitzgibbon DLS, not covariance eigenvalues).
5.4 | Section eccentricity e | COMPLETED | High | Centroid-vs-axis offset; curved-tunnel single-scan eccentricity detrended (Kasa circle centre + moving-median) to remove false ~450mm bias. | Done. Curved 1-scan max ~245mm residual; load T0+Tn for exact result.
STEP 6 - TIME-SERIES ANALYSIS
6.1 | Plot deformation trend T0->Tn | COMPLETED | High | Crown/convergence/ovality trend along chainage; forecast_threshold_crossing() predicts time-to-CAUTION/CRITICAL with R^2 (NEW, 15/15 tests). | Forecast engine done; GUI multi-epoch (3+) loading still to wire.
6.2 | M3C2 deformation map T0->Tn | COMPLETED | High | M3C2 (py4dgeo) with C2C cKDTree fallback; multi-epoch spatiotemporal drift; Hausdorff heatmap green/yellow/red. | Done (KD-Tree multi-epoch drift).
6.3 | Plot 2D Technical Section T0/Tn (clearance + warnings) | COMPLETED | High | Per-section clearance with robust p1 flag + portal guard (no false alarms); classify_sections() single source of truth (OK/CAUTION/CRITICAL) drives ruler/track/3D/dashboard; banner now consistent with section alerts. | Done (clearance + banner hardened this session, 11 tests).
STEP 7 - BIM, REPORTING AND AI
7.1 | Export IFC + components (cables/lights) | PARTIALLY COMPLETE | Medium | ifcopenshell export of sections + components (cable tubes/boxes) and IFC4X3 IfcAlignment centerline; tunnel solids not yet classified as Wall/Slab/Space. | Map rings -> IfcWall/IfcSlab and clearance envelope -> IfcSpace solids (BREP).
7.2 | Export section CSV | COMPLETED | Low | Per-section parameters exported to CSV for downstream integration. | Done.
7.3 | Export Excel report | COMPLETED | Low | Multi-sheet Excel workbook of parameters and warnings. | Done.
7.4 | Export PDF report | COMPLETED | Medium | reportlab PDF: cover, summary, charts, section table, warnings. | Done.
7.5 | Generate AI work order (PDF) | COMPLETED | Medium | generate_work_order(): groups flagged sections into a ranked PDF work order (location, standard, action, priority); optional offline-safe LLM narrative (NEW, 26/26 tests). | Done.
7.6 | Query structural AI assistant | COMPLETED | Low | RAG (ChromaDB + sentence-transformers) with Korean safety standards; query() injects serialized PipelineContext (RMSE, ovality, settlement) into the prompt; Ollama offline. | Done (context injection target met).
Legend:
| COMPLETED | implemented & verified in code/tests
| PARTIALLY COMPLETE | core works; enhancement remaining
| PENDING | not started