## Gap Analysis
PROJECT PROGRESS & GAP ANALYSIS — TUNNELAPP V4.0
Osong Tunnel Monitoring Project ¦ CBNU Smart Structure Lab (SSL)
ID | Module / Feature Component | Current Status | Priority | Technical Deficit & Code Context | Target Resolution & Optimization Strategy (JIT)
LAYERS 1 & 2: BASE & PRE-PROCESSING LAYER (Data I/O & Filtering)
1.1 | Point Cloud File I/O | COMPLETED | Medium | Successfully parses .LAS formats using laspy and open3d packages. | Extend parser layer to natively support structured txt file types from industrial scanners (Trimble/Faro).
1.2 | SOR Filtering & Voxel Downsampling | PARTIALLY COMPLETE | Low | Statistical Outlier Removal (SOR) and voxel grid downsampling behave as expected via Open3D pipelines. | Optimize filtering execution via Numba JIT compiling loops if raw point cloud scaling exceeds 50 million coordinates.
1.3 | Automated Morphological Filtering | PARTIALLY COMPLETE | Low | Lacks robust algorithms to isolate structural anomalies and fixtures (cables, ventilation pipes) from the bare lining surface. | Incorporate design-profile distance threshold filters or heuristic cluster grouping to mask out internal objects.
LAYER 3: GEOMETRIC LAYER (Alignment & Kinematic Frame Extractor)
3.1 | B-spline Centerline Generation | COMPLETED | High | Implements Scipy splprep/splev routines to construct continuous second-derivative C² 3D trajectories smoothly. | Incorporate an automated centerline moving-average pre-filter to prevent minor local noisy scan drifts from corrupting frames.
3.2 | Tunnel Reference Frame (Frenet-Serret) | PARTIALLY COMPLETE | High | Current script uses a rigid global Z-up vector ([0,0,1]) causing mathematical twist discontinuities and skewed cross-sections at tight curves. | Implement a hybrid Kinematic Bishop / Rotation Minimizing Frame (RMF) to smooth the normal vector path and eliminate rotation discontinuities.
3.3 | Ring Segmentation (Cuts) | METHODOLOGY ERROR | High | Discretizes tunnel sections by sorting points into naive equidistant spatial projection boxes (bins) along the trajectory. | Align with the master PDF specification: Compute the numerical gradient of the LiDAR Intensity signal to extract concrete segment joints (Intensity Valleys).
LAYER 4: PARAMETER EXTRACTION (Structural Deformation & Engineering Metrics)
4.1 | Tunnel Ovality & Eccentricity | METHODOLOGY ERROR | High | Incorrectly evaluates shape distortion via covariance matrix eigenvalues (structural variance), which flags scatter density rather than physical geometry. | Integrate Fitzgibbon's Direct Least Squares Ellipse Fitting via 'cv2.fitEllipse' or 'skimage.measure.EllipseModel' on projected 2D coordinates to extract real axes (a, b).
4.2 | Deformation Heatmaps (3D) | LOGIC ERROR | High | Renders deviations based purely on internal coordinate variances inside isolated static epochs. | Transition to multi-epoch spatial Hausdorff Distance computation using KD-Trees (scipy.spatial.cKDTree) to evaluate actual coordinate drift over time.
4.3 | 2D Tunnel | PENDING | Medium | Lacks cylindrical unrolling processing to output continuous 360-degree flat inspection maps for wall crack localization. | Transform spatial parameters into polar-cylindrical maps (station, angle) to produce high-resolution flat 2D projection image arrays.
LAYER 5: AI / BIM & REPORTING LAYER
5.1 | IFC BIM Export | PENDING | Medium | IfcOpenShell integration scaffolded but tunnel geometry not yet mapped to IFC schema elements. | Map centerline, rings, and deformation vectors to IfcAlignmentCurve + IfcStructuralSurfaceMember entities.
5.2 | RAG / AI Assistant | PARTIALLY COMPLETE | Low | LLM query pipeline exists but retrieval context does not include computed structural metrics. | Inject serialized PipelineContext (RMSE, ovality, settlement deltas) into RAG prompt at query time.