## Gap Analysis
PROJECT STATUS & GAP ANALYSIS — TUNNEL ANALYSIS v4.0
Osong Tunnel Monitoring Project ¦ CBNU Smart Structure Lab (SSL) ¦ Code-verified status as of 2026-06-08
ID | Module / Feature Component | Current Status | Priority | Current Code Status (evidence) | Remaining Work / Optimization
LAYERS 1 & 2: BASE & PRE-PROCESSING (Data I/O & Filtering)
1.1 | Point Cloud File I/O | COMPLETED | Medium | Parses .las/.laz/.ply and .txt/.xyz/.pts/.csv (io_layer.py); RGB to luminance fallback; multi-station + multi-epoch (T0/Tn) load. | Done. Optional: native E57 / vendor headers (Trimble/Faro).
1.2 | SOR Filtering & Voxel Downsampling | COMPLETED | Low | Open3D voxel grid + adaptive statistical outlier removal; voxel recenters only for a single scan so multi-station frames are preserved. | Done. Numba JIT only worthwhile if raw cloud exceeds ~50M points.
1.3 | Automated Morphological / Semantic Filtering | COMPLETED | Medium | auto_denoise() removes cables (linearity), lights (sphericity), people (DBSCAN) via vectorized local-PCA Demantke features + sanity guards; wired into AUTO PIPELINE (step 2.5). | Done. Future option: deep-learning segmentation (PointNet++/RandLA-Net) for hard cases.
LAYER 3: GEOMETRIC (Alignment & Kinematic Frame Extractor)
3.0 | Epoch Registration (T0/Tn alignment) | COMPLETED | High | register_epochs(): marker-based SVD when >=3 fixed markers (no deformation absorption) else trimmed-ICP; divergence-guard keeps result never worse than input. | Done (new). Roll about a round tunnel needs markers; yaw+translation recovered by ICP.
3.1 | B-spline Centerline Generation | COMPLETED | High | Scipy splprep/splev continuous C2 trajectory; curvature-guarded tangent refine kept only when it reduces the axis-centre offset. | Done.
3.2 | Tunnel Reference Frame (Frenet-Serret) | COMPLETED | High | Bishop parallel-transport, gravity-anchored twist-free frames (geometry.py) — eliminates the rigid Z-up twist discontinuity on tight curves. | Done (sample's RMF/Bishop target implemented).
3.3 | Ring Segmentation (Cuts) | COMPLETED | High | detect_ring_seams_by_intensity(): bins intensity along the axis, smooths, computes the 1st derivative and extracts joint valleys (segmentation.py), per PDF 3.3. | Done (intensity-valley method, not naive equidistant bins).
LAYER 4: PARAMETER EXTRACTION (Structural Deformation Metrics)
4.1 | Ovality & Eccentricity | COMPLETED | High | Fitzgibbon Direct Least-Squares ellipse fit (fit_ellipse_fitzgibbon, parameters.py) -> real major/minor axes (a,b); curved-tunnel eccentricity detrended. | Done (sample's Fitzgibbon DLS target implemented).
4.2 | Deformation Heatmaps / Hausdorff (multi-epoch) | COMPLETED | High | M3C2 (py4dgeo) with C2C cKDTree fallback; multi-epoch spatiotemporal_series evaluates real coordinate drift T0->Tn (not static variance). | Done (KD-Tree multi-epoch drift).
4.2b | Predictive Maintenance Forecast | COMPLETED | Medium | forecast_threshold_crossing(): fits deg-1/2 trend over epochs -> predicts time to CAUTION/CRITICAL with R^2 and rate (NEW this session, 15/15 tests). | Engine done; GUI multi-epoch (3+) loading still to wire.
4.3 | Clearance / Gauge Analysis | COMPLETED | High | Per-section vehicle-gauge clearance; robust 1st-percentile flagging (a lone stray point cannot condemn a section) + portal guard; auto-gauge from measured bore radius. | Done (hardened this session: percentile + portal guard, 11 tests).
4.4 | 2D Polar / Cylindrical-Unroll Map | PARTIALLY COMPLETE | Medium | Per-section polar deformation map (polar_map / polar_angles) computed; a full 360-degree flat unrolled panorama for wall-crack localization is not yet rendered. | Add (station, angle) flat panorama image export.
LAYER 5: AI / BIM & REPORTING
5.1 | IFC / BIM Export | PARTIALLY COMPLETE | Medium | ifcopenshell export of sections + components (cable tubes/boxes) and IFC4X3 IfcAlignment centerline; tunnel solids not yet classified as Wall/Slab/Space. | Map rings -> IfcWall/IfcSlab and clearance envelope -> IfcSpace solids (BREP).
5.2 | RAG / AI Assistant | COMPLETED | Low | RAG (ChromaDB + sentence-transformers) with Korean safety standards; query() injects serialized PipelineContext (RMSE, ovality, settlement) into the prompt; Ollama offline. | Done (context-injection target met).
5.3 | AI Work Order Generation | COMPLETED | Medium | generate_work_order(): groups flagged sections into a ranked PDF work order (location, standard, action, priority); optional one-line LLM narrative, offline-safe (NEW, 26/26 tests). | Done.
5.4 | Reporting (PDF / Excel / CSV) | COMPLETED | Medium | PDF (reportlab: cover, summary, charts, warnings, work-order cards), Excel 5-sheet, CSV export. | Done.
5.5 | Web Dashboard | COMPLETED | Low | Dash dashboard with interactive callbacks (click chart -> section detail, dropdown table filter) NEW; overall banner now consistent with per-section alerts. | Done (interactivity added this session).
STABILITY & ENVIRONMENT
6.1 | 3D Viewport (PyVista) | COMPLETED | High | Fixed false 'PyVista is not installed' (lazy-load import-* binding regression); runs on .venv Python 3.12 with PySide6 + pyvistaqt + vtk. | Done. Avoid .venv311 (vtk DLLs blocked by Windows app-control).
6.2 | Automated Test Coverage | COMPLETED | Medium | 20+ regression suites all passing: forecast, work order, clearance robustness/portal guard, consistency, ground-truth deformation, end-to-end pipeline. | Done. Keep extending as features land.
Legend:
| COMPLETED | implemented & verified in code/tests
| PARTIALLY COMPLETE | core works; enhancement remaining
| PENDING | not started